## WBS
Work Breakdown Structure | [8 empty] | CSI: Psicometric tests
| Project Start | 2019-02-05
Level | WBS | Task Description | Assigned To | Estimated Time in days | Net Working Days | Effort | Start | End | Notes
1 | 1 | D2D Design to Develop
2 | 1.1 | Analysis and Design | Juan Carranza | 1 | 1 |  | 2019-02-05 | 2019-02-05 | General perspective CPAR Understanding.
2 | 1.2 | Design and create configuration file | Juan Carranza | 1 | 1 |  | 2019-02-06 | 2019-02-06 | 1. Config File Name: Conexiones_Aplicativos.xlsx 2. Process triggered by email with subject = CSI_ADT_RESULTADOS_PRUEBAS_PSICOMETRICAS CSI_ADT_ENVIO_PRUEBAS_PSICOMETRICAS 3. Define variable, constants, credentials, auxiliary files, etc. 4. Occurrence on a daily baisis, Excution date can be configurable, default date = Today()
2 | 1.3 | Download standard template | Juan Carranza | 2 | 2 |  | 2019-02-07 | 2019-02-08 | 1. Credentials will be stored on config file 2. Download "Envio pruebas psicometricas" file from AuraPortal.
2 | 1.4 | Send Amitai Test | Juan Carranza | 2 | 2 |  | 2019-02-11 | 2019-02-12 | 1. https://www.amitaisystem.com 2. Credentials will be stored on config file. 3. Refer to seccion B1 on CPAR
2 | 1.5 | Send PCA Test | Juan Carranza | 2 | 2 |  | 2019-02-13 | 2019-02-14 | 1. https://timshr.com 2. Credentials will be stored on config file. 3. Refer to seccion B2 on CPAR
2 | 1.6 | Send MIL Test | Juan Carranza | 4 | 2 |  | 2019-02-15 | 2019-02-18 | 1. https://milrrhh.timsinternational.net 2. Credentials will be stored on config file. 3. Refer to seccion B3 on CPAR
2 | 1.7 | Register "Sent Test" in BPM | Juan Carranza | 2 | 2 |  | 2019-02-19 | 2019-02-20 | 1. Credentials will be stored on config file. 2. Register the "Sent Test" accordingly to the psicometric test (MIL, AMITAI, PCA) 3. Refer to seccion B4 on CPAR
2 | 1.8 | Notification of Done Amitai | Juan Carranza | 2 | 2 |  | 2019-02-21 | 2019-02-22 | 1. Open Mailbox 2. Read email with subject "Evaluacion de Integridad Terminada" and sender "AMITAI INFORMA". 3. Identify "Id", "Nombre" and "Apellido" from the body of the email. 4. Refer to seccion C1 on CPAR
2 | 1.9 | Notification of Done PCA | Juan Carranza | 2 | 2 |  | 2019-02-25 | 2019-02-26 | 1. Open Mailbox 2. Read email with subject "PCA Completo" and sender "pca@timshr.com". 3. Identify candidate's email from the body of the email. 4. Refer to seccion C2 on CPAR
2 | 1.10 | Notification of Done MIL | Juan Carranza | 2 | 2 |  | 2019-02-27 | 2019-02-28 | 1. Open Mailbox 2. Read email with subject "Tims - notificacion prueba MIL" and sender "TIMS". 3. Identify candidate's ID from the body of the email. 4. Refer to seccion C3 on CPAR
2 | 1.11 | Download test results Amitai | Juan Carranza | 5 | 3 |  | 2019-03-01 | 2019-03-05 | 1. Access to Amitai portal. 2. save the results as pdf. Filename = "nombre y apellido del evaluado" 3. Refer to seccion D1 CPAR Exceptions section.
2 | 1.12 | Download test results PCA | Juan Carranza | 3 | 3 |  | 2019-03-06 | 2019-03-08 | 1. Access to PCA portal. 2. save the results as pdf. Filename = "nombre del reclutador" 3. Refer to seccion D2 CPAR Exceptions section.
2 | 1.13 | Download test results MIL | Juan Carranza | 3 | 3 |  | 2019-03-11 | 2019-03-13 | 1. Access to MIL portal. 2. save the results as pdf. Filename = "nombre del reclutador" 3. Refer to seccion D3 CPAR Exceptions section.
2 | 1.14 | Upload results to AuraPortal | Juan Carranza | 2 | 2 |  | 2019-03-14 | 2019-03-15 | 1. Access to AuraPortal. 2. Refer to seccion E CPAR Exceptions section.
2 | 1.15 | Exception Handling | Juan Carranza | 1 | 1 |  | 2019-03-18 | 2019-03-18 | 1. Refer to Business and System Exceptions on CPAR.
2 | 1.16 | UAT | Juan Carranza | 7 | 5 |  | 2019-03-19 | 2019-03-25
2 | 1.17 | UAT Sign-Off | Jose Morales | 1 | 1 |  | 2019-03-25 | 2019-03-25
1 | 2 | Handover and Deployment
2 | 2.1 | Deploy to Production | Juan Carranza | 1 | 1 |  | 2019-03-26 | 2019-03-26
2 | 2.2 | Artifact Operational Handbook AOH | Juan Carranza | 2 | 2 |  | 2019-03-27 | 2019-03-28
2 | 2.3 | Handover | Juan Carranza | 4 | 2 |  | 2019-03-29 | 2019-04-01
1 | 3 | Go-Live
2 | 3.1 | Hypercare | Juan Carranza | 7 | 5 |  | 2019-04-02 | 2019-04-08
2 | 3.2 | Project Sign-Off | Donald Pineda | 7 | 5 |  | 2019-04-02 | 2019-04-08
◄ Add new rows ABOVE this one.
Formulas:
Net Working Days = NETWORKDAYS([Start],[End])
End = IF(ISBLANK([Start]),"",[Start]-1+ IF([Estimated Time in days]<1,1,[Estimated Time in days]))